## Sheet1
charter	4	a
scheduling	4	b
sequence diagram	4	c
class diagram	4	d
database planning (product)	3	e-1
database planning(supplier)	3	e-2
database planning(customer)	3	e-3
database planning(cost center)	3	e-4
database planning(inventory station)	3	e-5
database planning(employee)	3	e-6
database planning(job order lib)	3	e-7
database planning(return)	4	e-8
database planning(pending)	4	e-9
database planning(par)	4	e-10
bdd for add item(save to database)	4	F-bdd
test case for add item (save to database)	4	F-tc
Coding for add item (save to database)	4	F-cod
coding for add item (IRR)	4	F-code
UI (IRR)	4	F-ui
integration for add item	4	F-in
bdd for edit item(save to database)	4	G-bdd
test case for edit item (save to database)	4	G-tc
Coding for edit item (save to database)	4	G-cod
UI edit item (IRR)	4	G-ui
integration for edit item	4	G-in
bdd for withdraw(PAR)	4	H-bdd
test case for withdraw item (PAR)	4	H-tc
coding for withdraw item (PAR)	4	H-cod
UI (PAR)	4	H-ui
integration for withdraw item(PAR)	4	H-in
bdd for withdraw(MIV)	4	I-bdd
test case for withdraw item (MIV)	4	I-tc
coding for withdraw item (MIV)	4	I-cod
UI (MIV)	4	I-ui
integration for withdraw item(MIV)	4	I-in
bdd for withdraw item (WRS)	4	J-bdd
test case for withdraw item (WRS)	4	J-tc
coding for withdraw item (WRS)	4	J-cod
UI (WRS)	4	J-ui
integration for withdraw item(WRS)	4	J-in
bdd for withdraw item (GARV)	4	K-bdd
test case for withdraw item (GARV)	4	K-tc
coding for withdraw item (GARV)	4	K-cod
UI (GARV)	4	K-ui
integration for withdraw item(GARV)	4	K-in
bdd for return confirmation	4	L-bdd
test case for return confirmation	4	L-tc
coding for return confirmation	4	L-cod
UI (return confirmation)	4	L-ui
integration for return confirmation	4	L-in
overall integration	4	m
overall testing	4	n
deploy	4	o
dummy activity	4	p